[Proposal]
Current software translation activities are all scheduled within Alpha phase. Besides active development occurs after Alpha. This often leads string freeze breaks. The breaks informed to us are translated but have to rely on translator's great flexibility. For silent breaks, simply not translated as no one notice. In order to coordinate translators resource more manageable, and to achieve higher localization percentage for Final Release (GA), G11N would like to move all software translation related events after Beta Freeze date. Please notice that this moves 'Software String Freeze' same date of Beta Freeze, thus allows the developers to change/add/remove strings freely to the last minute without soliciting to translation team.

The impact to other teams;
Devel – due to string freeze date change, no more rebuild translation in Alpha phase, but Launch phase.
RelEng – no longer need to compose the image for l10n-qa, as Beta PA can be utilized instead.

Affected events;
- Software String Freeze
- Software Translation
- Software L10N QA Test
- Software Translation Deadline
- Software Rebuild all translated packages by maintainers

As example, applying to current F23 Key Milestones looks like below;

[Example with F23 key milestones]
2015-05-26	Fedora 23 Release
2015-06-23	Change Checkpoint: Proposal submission deadline (System Wide Changes)
2015-xx-xx	Side Tag Builds Deadline
2015-06-16	Mass Rebuild
2015-07-14	Branch Fedora 23 from Rawhide (Rawhide becomes future F24)
2015-07-28	Alpha Freeze (*)
2015-07-28	Software String Freeze
Change Checkpoint: Completion deadline (testable)
Bodhi activation point
2015-08-11	Alpha Release
2015-08-25	Software Translation Deadline
2015-09-08	Beta Freeze (*)
2015-09-08	Software String Freeze
2015-09-08	Change Checkpoint: 100% Code Complete Deadline
2015-09-22	Beta Release
2015-09-22	Software L10N QA Test (2015-09-22 to 2015-09-29)
2015-09-30	Software Translation Deadline
2015-09-30	Software: Rebuild all translated packages (2015-09-30 to 2015-10-07)
2015-10-13	Final Freeze (*)
2015-10-27	Fedora 23 Final Release